## Sheet1
| Task Name | Duration (working days) | Start | Finish | Dilvery dates
Design (Wireframes)
1 | Home page design | 6 | 2007-10-29 | 2007-10-06 | 2007-10-06
2 | caGrid discovery design | 6 | 2007-11-07 | 2007-11-16
| directory view page design |  |  |  | 2007-11-16
Search (field search)
3 | Query Design | 6 | 2007-11-19 | 2007-11-23
| building query design |  |  |  | 2007-11-21
| history |  |  |  | 2007-11-23
results
| total days | 18
Visual design
1 | Home page design | 7 | 2007-10-05 | 2007-10-15 | 2007-10-15
2 | caGrid discovery design | 5 | 2007-11-16 | 2007-11-22
| directory view page design |  |  |  | 2007-11-22
Search (field search)
3 | Query Design | 5 | 2007-11-23 | 2007-11-30
| building query design |  |  |  | 2007-11-28
| history |  |  |  | 2007-11-30
results
| total days | 17
UI implementation
1 | Home page design | 5 | 2007-10-19 | 2007-10-23 | 2007-10-23
2 | caGrid discovery design | 5 | 2007-11-26 | 2007-11-30 | 2007-11-30
directory view page design
Search (field search)
3 | Query Design | 5 | 2007-12-03 | 2007-12-07
| building query design |  |  |  | 2007-12-05
| history |  |  |  | 2007-12-07
results
| total days | 15