## Sheet1
Release | User | Iteration | GForge Task No. | Priority | Level of Effort (Days) | Description
caGrid 1.1 | User Community |  | RFE #4669 | High | 10 | When users create services with Introduce, they must currently manually edit the generated standard service metadata file to populate their contact and research center information. This should be editible with a custom GUI in Introduce, both during service modification, and also deploy time. The contact information itself should come from the information available in the caDSR.
caGrid 1.1 | User Community |  |  | High | 2 | Introduce will add support to add documentation tags to all components of the service (methods, parameters, etc), which exist in the service metadata but didn't used to exist in the Introduce model. The metadata generation needs to make use of these new feilds.
caGrid 1.1 | Internal |  |  | Medium | 10 | Need common GUI components for service discover for use in other GUIs (introduce, security Uis, etc)
caGrid 1.1 | User Community |  |  | Medium | 2 | Add the ability to disable registration to Index Service during deployment (for local testing)
caGrid 1.1 | Internal |  | RFE #4447 | Medium | 5 | When caGrid 1.0 Introduce created services are opened with caGrid 1.1 Introduce, the documentation information in their metadata should be merged into their Intrdouce model and not lost. (Metadata extension upgrader)
caGrid 1.1 | Internal |  | RFE #4149 | Medium | 10 | Introduce users who did not use the caCORE SDK should be able to have Introduce generate them java classes, XSDs, and configure serialization from a model (XMI file)
caGrid 2.0 | User Community / Internal |  |  | High | 50 | Enhance the GME to address identified limitations (allow cyclic package dependencies, allow encorement of policy (prevent cyclics, unregistered types, etc), support schema update/delete, support lifecycle to facilitate development cycle and schema retirement, access control)
caGrid 2.0 | User Community / Internal |  | RFE #4651 | Medium | 20 | Need a way to programmatically constrain services from publishing on the "production" caGrid, or enable discovery to filter out undesirable services This should require "some" administrative control
caGrid 2.0 | Internal |  | RFE #4476/4477 | High | 10 | Determine necessity of policy and enforcement on use of inheritance and abstract types. As serializing and deserializing subclass types requires serializers and deserializers for subclasses to be specified, and those subclasses can be defined at runtime (even by foreign schemas), their use could be abused such that a service or client may not actually understand how to process the data. May want to require a restrictive policy that limits the allowable use of "xsi:type".
caGrid 2.0 | Internal |  | RFE #3710 | High | 15 | Work with caDSR team to design UML to XML binding information, how to store and make available in caDSR, and the public interfaces which will be used to access it.
caGrid 2.0 | Internal |  |  | High | 5 | Integrate UML/XML binding infromation into caDSR grid service
caGrid 2.0 | Internal |  |  | High | 5 | Integrate UML/XML binding infromation into Introduce caDSR discovery component and data services (allows service developers to only be concerned with caDSR; ignoring GME and XSDs)
caGrid 2.0 | User Community / Internal |  |  | Medium | 5 | discovery enchancements to support "compliant services" and complex criteria
caGrid 2.0 | User Community |  |  | Medium | 10 | updates to standard metadata based on community needs, and backwards compatiblity plan
caGrid 2.0 | User Community |  |  | Medium | 20 | investigate additional semantic discovery (higher level APIs leveraging EVS internally)
caGrid 2.0 | caDSR |  |  | Medium | 30 | The caDSR is working to support leveraging services (standard service metadata), need to finish integration and close the loop such that services edited in Introduce are synchronized with registered information in caDSR (may need to support pulling annotated information from caDSR, or pushing changes to caDSR)
caGrid 2.0 | caTRIP |  |  | Low | 5 | Add the ability to register to multiple Index Services
caGrid 2.0 | Internal |  | RFE #3000 | Low | 5 | The GME database uses the keyword "schema," which was introduced in MySQL 5 as a reserved keyword.