## Sheet1
caGrid Security
Release | User | Iteration | GForge Task No. | Priority | Level of Effort (Days) | Description
1.1 | internal |  |  | medium | 20 | Add support for a Hardware Security Module (HSM) to Dorian.
1.1 | internal |  |  | high | 10 | Publish a Certificate Policy and Practice Statement for Dorian.
1.1 | internal |  |  | low | 5 | Modify Dorian to validate that all Idenity Providers certificates are signed by a trusted certificate authority
1.1 | internal |  |  | low | 2 | Review Installers for security services
1.1 | internal |  |  | low | 1 | Modify Dorian to remove IFS users that are removed from the Dorian IdP
1.1 | internal |  |  | high | 2 | Modify Dorian to meet the Dorian CPS
1.1 | internal |  |  | low | 5 | Migrate Security UI(s) to the Grid Application Environment (GRAPE), including enhancements to GRAPE.
1.1 | internal |  |  | medium | 5 | Modify Grid Grouper to allows users to get a list of groups in which they are a member.
1.1 | internal |  |  | high | 10 | Integrate the BDT/GridFTP framework with the security infrastructure.
1.1 / 2.0 | internal |  |  | high | 40 | Design and Develop a solution for provisioning service/container ceritifcates / develop CPS if required.
1.1 / 2.0 | internal |  |  | med | 30 | Design and Develop a Delegation solution that can be leveraged by both Grid Services and web applications
1.1 / 2.0 | internal |  |  | med | 10 | Develop a generic login web application for authenticating users to web applications
2 | internal |  |  | low | 5 | Add service discovery to the security UI(s).
2 | avinash |  |  | med | 10 | CSM is planning developing a solution for providing instance level security with a reasonable performance and scalability. Integrate with solution in caGrid (Grid Grouper, PDP, etc).
2 | internal |  |  | low | 30 | Develop web application modules for using and administrating the security infrastructure.
2 | internal |  |  | med | 5 | Develop UI for creating and managing sync descriptions and syncing with the trust fabric
2 | internal |  |  | med | 1 | Support mechanism for disabling the SyncGTS cache.
2 | internal |  |  | med | 5 | Add bootstrapping method to Dorian for unlocking keys
2 | internal |  |  | low | 2 | Add proxy minimum length enforcement to Dorian
2 | internal |  |  | low | 5 | Investigate SAML 2.0 support in Dorian
2 | internal |  |  | med | ?? | Investigate Auditing for caGrid
2 | internal |  |  | med | ?? | Investigate Directory services /Generic Attribute support for caGrid
ongoing | internal |  |  | med | ?? | caGrid Training Program
ongoing | internal |  |  | high | ?? | Work with caGridPMA and implement policies set forth
ongoing | internal |  |  | high | ?? | Work with applications teams / organizations to integrate with the production security infrastructure. (ie caB2B (Rakesh), caTIES (Kevin), caIntegrator (Subha) and CTMS Interop (Josh)
ongoing | internal |  |  | high |  | Work with caGrid workflow team to help them adopt the security infrastructure
ongoing | internal |  |  | high | ?? | Review and provide consulting related to security to others developing caBIG applications.